## Sheet1
Title | Description | Status
Add search box to Edit Companies | When editing a company in the Edit Companies window, it can be difficult to find the company you are looking for. It would be nice if there was a search box at the bottom. | Completed - Mar 1, 2010
Highlight all in text fields | By default, all text boxes should select all text when given focus so that a user can immediately being overwriting what was already in there. | Completed - Mar 5, 2010
Default names for PDFs | When saving to PDF in the DocumentViewer window a default filename should be used. For example when printing quotes, the default Filename should be Quote #[num]-[rev].pdf. | Completed - Mar 10, 2010
Create global configs table | A lot of stuff that is currently hard coded should be moved into a central config storage. One solution would be to create a flat lookup table in the database that stores key-value pairs that could be read at startup and stored in a global hashtable for quicker lookups. Alternatively, a lookup utility could be created that goes to the database on every lookup just in case configs are changed while the program is running. | Completed - Mar 8, 2010 (still need to go through and remove hard codes throughout program)
Contact types | Contacts should be able to be of zero to many types. Currently they were only able to be one type. | Complete - Mar 15, 2010
Drag contacts between addresses | In the Addresses and Contacts screen it should be possible to drag a contact from one address into another. | OPEN
Use new AutoCompleteBox | Consider replacing comboboxes with text searches with the new AutoCompleteBox control that is included in the newest WPF Toolkit release. Docs at http://msdn.microsoft.com/en-us/library/system.windows.controls.autocompletebox(VS.95).aspx | WONTFIX
Reference numbers in invoices | Before the invoice system rewrite it was possible to add any number of reference numbers to an invoice such as PO, AFE, etc. This needs to be added back in. | Completed - Mar 9, 2010
Related invoice extras to items | The invoice extras section should actually be a system where extras costs can be attached to a specific line item and then printed inline with them on the final invoice. Currently they are not this way. | OPEN
Reorder invoice items | It should be possible to reorder invoice items so that the order the are printed on the invoice is customizable. This might be done with drag and drop in the DataGrid control. | OPEN
Move 'view' buttons | For stuff like quotes and invoices, it would be nice to have the "View printout" button in the yellow-ish bar that includes the save button so that it can be pressed without going back to the first tab all the time. | Completed - Mar 10, 2010
Press enter in currency fields | Most users I have observed will instinctively hit enter after they have enter a value into any of the fields that acces a dollar amount, likely expecting it to format it correctly. Currently nothing happens when they do this, so it would be nice if it did. | Completed - Mar 10, 2010
Accept metric or english measurements | The system should be able to accept both metric and imperial measurements as both are used. The system should ideally store in metric and convert to imperial upon request. | OPEN
Quote condition selection | When one of the quote condition text boxes receives focus, it should automatically check the checkbox associated with it if it isn't already, as it is expected that if the user is editing the text they intent to include the condition and might forget to check it manually. | Completed - Mar 10, 2010
Differentiate read-only textboxes | Some entry forms have read-only fields, but it isn't obvious that you can't edit them until you try. It would be nice to change the style of these boxes so that the user knows they aren't editable. | Completed – Mar 11, 2010
Itemized pricing for quotes | There should be a button or checkbox in the quotes section that changes the quote price text field and calculates the price based on the commodity movement and supplement costs. | Completed - Mar 16, 2010
Progress bar or output for PDF creator | When clicking the "Create PDF" button in the document viewer, the user is not given any indication of what is happening. It would be nice if there were a progress bar or output window showing what is happening. UPDATE: There is now a simplistic window that indicates what is happening when the create pdf button is clicked. | Semi-completed – Mar 20, 2010
Visual indicators after a save | There seems to be concern by users about knowing when they have and haven't saved their work. I good visual indicator that shows they have saved their work would be nice. | OPEN
Job loads section needs to show the commodity list | When creating loads in the job section, it would be nice if the list of commodities was shown so that they can quickly be added. | Completed - Mar 29, 2010
Job list page needs customer details box | On the job invoice page is a box that allows you to add any key-value pair to an invoice that can be used for displaying stuff such as PO# and AFE#. This needs to be copied to the jobs section. | Completed - March 29, 2010
Add a duplicate button for jobs | Most section have a "duplicate" button to allow for quickly creating new items based on the currently selected item. The jobs section does not | OPEN
Dispatch printouts need file and driver copies | When printing out a PDF a dialog or something better needs to ask if a "driver copy" needs to be included in the printout. | OPEN
Standardize on confirmation dialogs | There are many places in the system where there are "remove" or "delete" buttons. Some of these buttons will open a dialog box asking the user to confirm the action, but others do not. It should be the same behaviour everywhere. | OPEN