## Sheet1
ID | Issue | Status | Component | Description | Date opened | Last modified
1 | View dispatch doesn't work | OPEN | Jobs -> Dispatches | The document created when pressing the "View dispatch" button is just a static sample document rather than content generated from the actual dispatch. | 2010-03-08 | 2010-03-08
2 | Import loses customer type | FIXED | Importer | The importing process does no mark what type of customer type each company is any more. | 2010-03-08 | 2010-03-15
3 | Search crash in Edit Companies window | FIXED | EditCompaniesWindow | Searching for a company that doesn’t exist will case a crash. | 2010-03-08 | 2010-03-08
4 | DatePicker controls look strange | FIXED | All | After updating to the latest WPF Toolkit, the DatePicker controls all look disabled, even when they shouldn't be. Note1: It appears that this is a bug with WPF Toolkit, so I will just wait until they fix it. Note2: I have fixed this issue by switching to the DataGrid and DatePicker controls in .net 4.0 | 2010-03-09 | 2010-03-18
5 | Images missing from PDF output | WORKAROUND | DocumentViewer | The wkhtmltopdf application seem to break images with a 'file://' url when converting to PDFs. This is likely a bug that I can't easily fix, so in the final version the required images will need to be placed on an HTTP server. | 2010-03-10 | 2010-03-15
6 | Contact types are imported | FIXED | Importer | The importing process does no add the contact types to imported contacts. | 2010-03-14 | 2010-03-15
7 | DatePicker don't show time | OPEN | Jobs section | In some subsections of the Jobs section there are places where both a date & time are required. By default the DatePicker control doesn't show the time, so I have placed a second TextBox control below with a time string format. Unfortunately, changing the time in the textbox will reset the date in the DatePicker and changing the date using the picker will reset the time. A DatePicker control that also shows the time would be ideal. | 2010-03-21 | 2010-03-21
8 | Creating PDFs causes application to lock until complete | FIXED | DocumentViewer | When creating a PDF from the document viewer, the entire application will lock up and stop repainting itself until the PDF is completely built and opened. This doesn't look of feel very polished. [FIX: the PDF application now runs a background thread and a message windows is now opened to indicated what is happening] | 2010-03-20 | 2010-03-23
9 | Switching companies sometimes doesn't update the job list | FIXED | Jobs -> Job List | To reproduce, make sure a job already exist in the system and used the "go to job" shortcut to get to it, then change companies and watch as the job list doesn't update. | 2010-03-25 | 2010-03-29
10 | Remove button always disabled for Loads | OPEN | Jobs -> Loads | There is currently no way to remove a load from a job as the remove button is always disabled. | 2010-03-29 | 2010-03-29