## Sheet1
ID | Issue | Status | Component | Description | Date opened | Last modified
1 | View dispatch doesn't work | OPEN | Jobs -> Dispatches | The document created when pressing the "View dispatch" button is just a static sample document rather than content generated from the actual dispatch. | 2010-03-08 | 2010-03-08
2 | Import loses customer type | FIXED | Importer | The importing process does no mark what type of customer type each company is any more. | 2010-03-08 | 2010-03-15
3 | Search crash in Edit Companies window | FIXED | EditCompaniesWindow | Searching for a company that doesn’t exist will case a crash. | 2010-03-08 | 2010-03-08
4 | DatePicker controls look strange | WONTFIX | All | After updating to the latest WPF Toolkit, the DatePicker controls all look disabled, even when they shouldn't be. (It appears that this is a bug with WPF Toolkit, so I will just wait until they fix it.) | 2010-03-09 | 2010-03-09
5 | Images missing from PDF output | WORKAROUND | DocumentViewer | The wkhtmltopdf application seem to break images with a 'file://' url when converting to PDFs. This is likely a bug that I can't easily fix, so in the final version the required images will need to be placed on an HTTP server. | 2010-03-10 | 2010-03-15
6 | Contact types are imported | FIXED | Importer | The importing process does no add the contact types to imported contacts. | 2010-03-14 | 2010-03-15